## Slide 1: Havant Borough Council Performance report
Q3 2020-21

## Slide 2: Contents
Headline achievements for Q3
People – key statistics for Q3
Finance
Update on corporate projects
Corporate governance – key statistics for Q3
Service dashboards (containing in-depth information about Corporate Action Plan objectives, KPIs, and budget variance)
Corporate Services
Regeneration & Place

## Slide 3: Headline achievements in Q3
We continued to provide support to residents and businesses during another national lockdown in November and the introduction of tier 4 restrictions in December
Cabinet approved the approach regarding the Langstone Flood and Coastal Risk management approach
The sale of former landfill site Brockhampton West was approved by Cabinet in November – the site, which has been earmarked for commercial development, will bring much needed jobs and investment to the area
We took community events online, with a virtual job fair helping residents look for new work opportunities

## Slide 4: People – key statistics for Q3
Number of new starters
Total FTE at end of quarter
Average number of sick days per FTE
Public sector average: 2.2 days Private sector average: 1.8 days
Number of leavers
Turnover rate
1.74
230
2
1
0.43%
3 most common reasons for short-term sick leave
Cough/cold/flu (11 sick days)
Operation/recovery (8 sick days)
Gastrointestinal problems (7.5 sick days)
Notes: The 2 new starters were in the Comms/Community Engagement team and the Executive Team
The 1 leaver was from the Development Management team
Turnover rate is calculated as the number of leavers as a % of the total FTE
We are now separating short term and long term sickness to be able to understand the most common reasons for sickness without the data being skewed by a small number of staff being off for a large number of days (e.g. for operation/recovery). Short term sickness is defined by the HR team as less than 21 days
Average number of sick days per FTE still includes both short and long term sickness
It should also be noted that these figures relate to those staff who are employed by HBC and therefore may not provide an accurate picture when comparing to the EHDC figures given that many staff are shared across both organisations and which authority they are employed by is largely a matter of chance. This will be addressed as we implement the One Workforce programme

## Slide 5: Finance – revenue budget outturn in Q3
 | Current Budget | Q3 Year End Forecast | Q3 Variation to Q2
 | £'000 | £'000 | £'000
Net Cost of Services | 14.591 | 16.015 | 0.091
Funding | (14.591) | (16.771) | (0.622)
Net (Surplus) / Deficit | 0 | (0.756) | (0.531)

## Slide 6: Finance – capital programme outturn in Q3
 | 2020/21 Budget | 2020/21 Provisional Outturn | 2020/21 Variance
 | £ (000) | £ (000) | £ (000)
Housing | 1.628 | 1.628 | 0
Operational Land and Buildings | 5.230 | 6.267 | 1.037
IT Equipment | 0.077 | 0.050 | (0.028)
Total Capital Programme | 6.935 | 7.945 | 1.010
 | 2020/21 Budget | 2020/21 Provisional Outturn | 2020/21 Variance
 | £ (000) | £ (000) | £ (000)
Funded By: |  |  | 
REFCUS (Revenue funded as Capital under Statute) | 1.628 | 1.628 | 0
External Grants & Contributions | 5.045 | 6.062 | 1.017
Use of Specific Reserves | 0.127 | 0.120 | (0.007)
Use of Capital Receipts | 0.135 | 0.135 | 0
Borrowing Requirement | 0 | 0 | 0
Total Funding | 6.935 | 7.945 | 1.010

## Slide 7: Corporate projects
Project | Purpose | Q3 update
Future Exchequer and Procurement service | Negotiations to remove from contract to ensure improvements in service | Negotiations concluded and report submitted to Cabinet for the resolution of outstanding disputes, milestones and volumetrics, and the removal of Exchequer and Procurement services from the contract. Procurement successfully withdrawn from the contract on 31st December 2020
Payroll system project | Procurement and delivery of payroll service and migration of software solution | Plan to extend current arrangement – Cabinet paper scheduled for mid February
Building Control – Tascomi implementation | Final outstanding milestones to deliver the Tascomi system | The data export/import issues are still outstanding. Staff have been working with the external suppliers to resolve outstanding matters and the data import and testing is now due January 2020
Building Control – service review | Ensuring service is effective and fit for purpose | Service review complete 2nd November. All staff now part of one workforce / one team across both Councils
Interim workstyle solutions | Co-ordinating next steps for new ways of working for reception and back office at Plaza and Penns Place | Delayed due to another national lockdown
Finance service improvement | Ensuring improvements following service returning to inhouse provision | Service review completed with new team structure advertised and existing team members subject to job evaluation
Digital committee meetings | Enabling digital committees as part of response to Covid 19 | Digital Committees are continuing through Skype for Business with increased engagement from the general public.
Waste collection implications of Environment Bill | Negotiating with HCC on efficiency savings implications | County-wide briefings took place during the quarter and work at local and county-wide level is progressing on schedule

## Slide 8: Corporate projects (continued)
Project | Purpose | Q3 update
Transformation programme | Definition of vision and purpose | Transformation programme being reviewed with structure to be put in place to take forward
Property – service review and system replacement | Design of service and procurement of digital solution to ensure fit for purpose | Service review completed and currently recruiting to vacant posts. New IT system to be taken forward in 21/22
Microsoft Teams implementation | Replacing Skype for Business with Microsoft Teams | Teams now rolled out across officers
Planning, Land Charges, Environmental Health – system replacement (DSIP) | Redesign and system implementation project (case management system) | Will be taken forward as part of transformation
Legal system replacement | Upgrade of Iken system to allow team to track and monitor cases | System upgrade is currently progressing working with IKEN team/Capita and Legal Services to ensure system meets requirements.
Digital Strategy | Numerous projects to deliver the strategy (including embedding of Sharepoint) | Will be taken forward as part of transformation

## Slide 9: Corporate projects (continued)
Project | Purpose | Q3 update
Outbreak Control Plan | Required for any possible local Covid outbreaks | Environmental Health team focussed on current lockdown and working with businesses to ensure lockdown regulations are followed accordingly
Covid-19 recovery programme | Ensuring that the health of communities and businesses is restored after the pandemic | On hold due to LRF moving back into response
Review of Constitution | Implementation of new Constitution | Constitution to be take forward for approval in Q4.
Leisure provision review | Negotiation over Horizon and future leisure provision | Not progressed during Q3
CVW decommissioning | Decommissioning virtual IT environment to allow for future ways of working | New laptop rollout progressed during quarter with additional devices allocated
Legal – service review | Implement agreed structure and recruit to vacant posts | Team review complete and out to recruitment. Further recruitment in early Q4 as initial recruitment was not successful
Licensing – service review | Resourcing review of service | Not progressed during Q3
Plaza replacement kiosk | Replacement of payment kiosk | Not progressed during Q3

## Slide 10: Corporate governance – key statistics for Q3
Number of complaints received
% of complaints resolved within 10 working days – target 85%
Number of information requests received (FOI, EIR and SAR)
186
Number of internal audit management actions overdue by more than 60 days
17
67% (Corporate)
76% (Norse)
46 (Corporate)
55 (Norse)
Notes: Most common areas for complaints in Q2 were:
Number of information requests has increased by 45% compared to Q1 – this is perhaps due to the easing of lockdown leading to more activity in economy, housing market, local politics etc

## Slide 11: Risks currently scoring above 16 on the corporate risk register
A residual score of 16 is the threshold which has been set to indicate the Council's risk appetite (as per the Risk Management Framework).
Risk ID | Risk Title | Type | Category | Identification of areas where there are significant risks | Date Added | Risk Owner | Original Assessment |  |  | Planned Mitigation Actions | Mitigation Success Factor | Control Assessment |  | 
 |  |  |  |  |  |  | L | I | P |  |  | L | I | P
HB6 | Medium Term Financial Strategy (MTFS) | FINANCIAL | Economic | The ongoing viability of the authority being able to manage a balanced budget. Current MTFS highlights a shortfall of £12M over the course of the MTFS | 28/11/16 | Lydia Morrison | 4 | 5 | 20 | 1. MTFS is reviewed each year as part of budget setting exercise. Budget challenge sessions held each year to scrutinise future business plans and income/savings. 2. Full MTFS review to take place in 2020/21 to alongside the Transformation programme 3. Identify and manage in-depth service budgets income/expenditure to rebalance budget 4. Consider the impact of Covid-19 on the MTFS | The authority has a balanced budget | 4 | 5 | 20
HB8 | IT Provision: short term | SERVICE | Technological | Failure by the IT provider (Capita) to provide good IT service to staff which results in a considerable regular downtime of IT leading to slower service provision. We become unable to provide a reliable and timely service to our customers. | 10/04/18 | Sue Parker | 4 | 5 | 20 | 1. Weekly IT Ops Board (every Monday) tracks progress on major issues and monitors progress. Weekly RAG progress score provided on all P1 and P2 calls from IT service centre. 2. Business Solutions continue to work with Capita and the teams to help address any issues identified. 3. Contractual triggers if escalation of incidents. | Reduction in P1 incidents through monitoring of Capita KPIs | 4 | 4 | 16
HB9 | IT Provision: long term | SERVICE | Technological | Failure by the IT provider (Capita) to deliver on long term digital vision and aspirations of Council as per the contract in particular the strategy for 'digital by default' and contract requirements | 10/04/18 | Sue Parker | 5 | 5 | 25 | 1. Ensure Capita are held to contractual responsibilities regarding digital strategy 2. Progression of a Digital Strategy for the Council as part of transformation with linkages to IT Capita 3. Renegotiation of IT contract in order to deliver required digital vision | Clear vision and links to Council aspiration of 'digital by default' Approval of Council's Digital Strategy | 4 | 4 | 16
HB10 | Corporate Project Delivery | GOVERNANCE | Reputation | Failure to maintain control of corporate project delivery leading to lack of clarity on priorities, use of resources resulting in reputational damage and potential costs and potential adverse impact on performance. | 07/05/18 | Gill Kneller | 4 | 5 | 20 | 1) Establishment of Strategic Project Board for oversight of key corporate projects 2) Clear review of project milestones to ensure on track and delivering as per budget 3) Dedicated project budget monitoring - in particular Capital budget monitoring 4) All corporate projects have appropriate governance in place and regularly produce highlight reports 5) Review of Corporate projects to ensure focus and resource is on the right project areas covering Corporate Strategy, transformation and Covid-19 recovery | Corporate projects will deliver on time or be replaced by others with greater importance | 4 | 4 | 16
HB15 | Cyber Attack – System failure | SERVICE | Technological | The Councils IT systems are brought down due to an external malicious attack leading to unavailability of information, case files, workflow and data required to run services resulting in delays and non-delivery; reputational impact; negative impact to customers requiring Council services and support, and a requirement on the Council to report an ‘availability breach’ to the ICO | 30/01/19 | Sue Parker | 4 | 5 | 20 | 1) Capita to evaluate and implement data centre defences to reduce likelihood and impact – see Cyber Security Action Plan 2) Business Continuity Plans in place for all services which reflect complete loss of IT system (linked to IT provision: short term) | All actions in Cyber Security Action Plan completed and business continuity plans all updated and accessible | 4 | 5 | 20

## Slide 12: Corporate Services dashboards
Performance information for Q3
Commercial Development
Customer Services
Finance
Legal
Organisational Development
Programmes, Redesign & Quality
Strategic Commissioning

## Slide 13: Commercial Development Head of Service: Chris Bradley
Budget variance in Q3
Corporate Action Plan 2020-21
Action | Outcome | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Develop and implement the first phase of the transformation programme | Clearly defined and articulated transformation workstreams with plans and resources in place to deliver transformation as per the timescales |  | Not reported | Worked with new transformation consultant to take forward programme | 
Variance of £51,000
Chart: 
| Q1
Budget | -2
Estimated outturn | -44

## Slide 14: Customer Services Head of Service: Brian Wood
Variance of -£91,000
Budget variance in Q3
Incorporating: Corporate Support, Elections, Land Charges, GIS, Insight
Customer Services and Revenues and Benefits are provided by Capita
Indicator | Target | Q1 | Q2 | Q3
Calls answered and completed by CSC - one and done (%) | above 95% | 99% | 100% | 99%
Calls answered within 20 seconds in the CSC (%) | above 75% | 61% | 76% | 86%
Council tax cash collection rate - cumulative (%) | above 98.9% (year end cumulative) | 28.9% | 47.2% | 74.7%
Non domestic rates cash collection rate - cumulative (%) | above 98.6% (year end cumulative) | 22.9% | 38.0% | 63.4%
Average processing time - housing benefit and council tax benefit change events (days) | below 7 | 5.3 | 4.8 | 4.5
Average processing time - housing benefit and council tax benefit - new claims (days) | below 17 | 10.0 | 10.0 | 10.8
Key Performance Indicators
Chart: 
| Q1
Budget | -2801
Estimated outturn | -2710
Notes: Council tax cash collection rate remains slightly below same time last year (47.97%) due to Covid 19
NNDR cash collection rate is significantly below same time last year (47.06%) due to Covid 19

## Slide 15: Customer Services
Team | Action | Outcome | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Corporate Support | Introduce new working arrangements to support the Covid response and transformation of the organisation | Team provides greater support to services across the office to assist with transformation of services |  |  | Team focused on Covid grant distribution in a timely manner. Numerous grant schemes currently being managed including track and track and business grants | 
Elections | Implement new canvass process | Improved data matching with central government records |  |  | Completed | 
Insight | Provide the organisations with insight and evidence to inform transformation, service delivery and Covid response work | Evidence based decisions are clearly demonstrated in organisational work |  |  | Continued work supporting the Covid response including additional residents survey distributed during the quarter | 
Land Charges | Continue to provide service alongside further digitisation of paper records | Improved income and streamlined processes through digitisation of paper records |  |  | Due to Government policy re stamp duty significant uplift in income during the quarter as reported in financial forecast | 
Revenues & Benefits | Review Discretionary Rate Relief guidelines to ensure they align with Corporate Strategy and financial sustainability | New Discretionary Rate Relief guidelines that align with Corporate Strategy and financial sustainability |  |  | Focus has been on Covid grant distribution | 
Corporate Action Plan 2020-21

## Slide 16: Finance Head of Service: Matthew Tiller
Corporate Action Plan 2020-21
Action | Outcome | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Review finance processes and procedures and implement all internal audit recommendations | Transformed team that is delivering required statutory functions with no outstanding internal audit recommendations |  |  | Continual review and improvement. Working to bring Exchequer functions inhouse for 1st April 2021, with review of processes. Service review to be completed for all of Finance before end of financial year | 
Progress budget, year-end and required statutory returns as per timetables | All activities achieved against timescales |  |  | Statutory deadlines met and budget setting on line with timetable. Only delay is HBC statement of accounts, where the audit has taken longer than anticipated. This is expected to be completed and signed in early 2021/22 | 
Review MTFS in light of Covid-19 | Financial sustainability of Council going forward is strong |  |  | MTFS updated as part of budget setting 2021/22. Work with Members and budget holders to identify pressures and potential savings to deliver balanced budget proposals for 2020/21 | 
Support the Council in delivery of its aims | Financial input is achieved at the right time for informed Council decisions on projects/programmes |  |  | Ongoing review of financial information to help inform estimated year end position. Continued review of income and regular submission to MHCLG for lost income. Work with budget managers to help decision making that allows the Council to come in on budget and set balanced budget for 2021/22 | 
Variance of £421,000
Budget variance in Q3
Chart: 
| Q1
Budget | -1480
Estimated outturn | -1901

## Slide 17: Legal Head of Service: Daniel Toohey
Corporate Action Plan 2020-21
Team | Action | Outcome | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Democratic Services | Fully integrate the HBC and EHDC Democratic Services teams | A single multi-skilled workforce supporting the democratic process across both Councils |  |  | New structure agreed with Unison, salary grade for new positions agreed by HAY Panel, recruitment exercise underway | 
 | Adopt the digital-by-design approach to meetings, agenda and papers | Reduced waste paper and more efficient services |  | complete | Complete | complete
 | Improve performance regarding: a) late submission of papers b) key decision notices c) report numbering d) publication targets | Measured performance targets |  |  | With management support a no late report policy is becoming embedded within the organisation | 
Legal Services | Review and build capacity of legal support for the Councils’ regeneration programme and asset income streams | Positive feedback Recruitment carried out re planning and projects Legal Services budget target for income; external counsel spend managed and procured compliantly | Not reported | Not reported | First round of recruitment now completed with one hire; second round about to commence. Vacancies being covered by agency staff in the interim | 
 | Review and support re legal advice and assistance for the Councils’ Covid-19 response including priority change programmes and transitional support programmes | Successful transition re constitutional changes and member and officer engagement Engagement with partners Delivery re governance changes e.g. virtual committee meetings, review of extension re Annual Council | Not reported | Not reported | Assisting client departments on Covid related work as and when instructions received. Constitutional changes now adopted by full Council and member and officer engagement. Training programmes for the benefit of Members being devised in light of adoption of remodelled Constitution | 
 | Oversee the review of the Constitution and policy framework in line with transformation objectives of the Council | Robust and viable Constitution with services having a greater understanding of policy framework which enables service delivery and delivers clear decision making | Not reported | Not reported | New Constitution now adopted by full Council to come into force 1 March 2021 | 
Incorporating: Legal Services, Democratic Services
Variance of -£52,000
Budget variance in Q3
Chart: 
| Q1
Budget | -392
Estimated outturn | -340

## Slide 18: Organisational Development Head of Service: Caroline Tickner
Incorporating: Human Resources, Communications & Marketing, Emergency Planning & Business Continuity, Health & Safety
Variance of £20,000
Budget variance in Q3
Corporate Action Plan 2020-21
Continued on next slide
Chart: 
| Q1
Budget | -1300
Estimated outturn | -1320
Team | Action | Outcome | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Communications & Marketing | Develop effective marketing campaigns (internal and external) for major projects in light of Covid-19 | Increased staff and resident satisfaction (with reports of good experiences) because services are understood and delivered in a convenient way (dependent on service delivery) |  |  | Continual focus on updating website and social media with latest coronavirus information. Promotion of the new rules to residents via website, e-newsletters and social media. Promotion of support packages available to businesses in the area via website, e-newsletter and social media. Signed up to social media channel Nextdoor to reach approximately 11,000 residents with our messages. Promotion of coronavirus survey to residents. Promotion of internal staff wellbeing survey | 
 | Develop innovative campaigns to encourage customers to use digital channels to boost channel shift away from telephone/paper and face-to-face interactions, building on the digital channel shift already achieved due to Covid-19 emergency | Increased access and ease of access to our services for our residents and businesses (dependent on customer access and digital strategies) |  |  | Website continuously updated with the latest coronavirus information and support available. Application forms created for business support grants. Complete overhaul of the out of hours information on the website. Brexit information on the website updated. Refreshed metatags on the website to improve search results. In Q3, we gained 1,581 subscribers to e-newsletters, 467 likes on Facebook, 66 followers on Twitter and 161 followers on Instagram. E-newsletter bulletins had an engagement rate of 82.8% (national average for local government is 62%) | 
 | Use a strategic basis for determining communications priorities and activity so that corporate priorities are linked to communications priorities Communications to be factored into service plans and linked directly to communications support for recovery following Covid-19 emergency | Informed, engaged and motivated employees and councillors (powerful Council ambassadors) who understand how their day to day work in the 'new normal' is delivering the Corporate Strategy. Informed public who have an understanding and appreciation for what the Council is trying to achieve |  |  | Insight-based communications and marketing approach developed for Warmer Homes campaign to target messages to ensure efficient and effective approach. Promotion of internal support for staff including Wellbeing Wins and future working arrangements | 

## Slide 19
Team | Action | Outcome | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Emergency Planning & Business Continuity | Lead the 'organisational' aspect of the Covid-19 recovery plan ensuring that this supports the overall recovery operating plan at a local and Hampshire-wide level and aligns with the wider scope of transformation | A robust organisational recovery plan which aligns with and complements the wider organisational transformation objectives |  |  | The rise in infection rate has led to the organisation moving out of recovery and back into response. Recovery work is now paused until the transmission rate reduces and the LRF stand down the emergency response | 
 | Provide the relevant training across the Council to ensure the responsibilities for BC & EP are understood by all and the Council can respond effectively should a disruption/emergency arise | Appropriate strategic and operational incident response and recovery |  |  | The BC and EP training sessions due to take place in October/November had to be delayed due to Covid workload. They have now been rescheduled for January and February. The EP training will include the new roles that are being introduced and the new message/tray system within the ECC. The district and borough plans are currently being updated by HCC EP and will be shared with the councils shortly | 
 | Fully understand the threats to the delivery of critical services at a local and national level and build an overall recovery plan for Covid-19 which ensures that critical services can continue to be delivered as the organisation moves from response to recovery following the Covid-19 emergency | Appropriate strategic and operational incident response and recovery |  |  | Continued response to changing Covid situations re tiered system and lockdown. Primary focus on the delivery of P1/P2 critical services; business continuity at the forefront. Move back into response may delay some aspects of the recovery work. On track for the continued delivery of critical services | 
Health & Safety | Actively promote the need for the Council and its contractors to comply with all aspects of H&S legislation, ensuring that relevant monitoring and reporting is in place to mitigate risk in line with Covid-19 requirements | Rigorous monitoring of the Council and its contractors to ensure compliance with all aspects of H&S, escalating through the relevant channels where necessary if compliance falls short of minimum regulatory standards |  |  | Continuing to attend monthly CMT (Client) meetings, raising outstanding actions in relation to required documentation. Also attending the monthly service meetings. Review has taken place of the Norse Kahootz area and we have established reporting mechanisms which allow Norse to update directly – this will enable an easier auditable process. On site inspections currently on hold. We have produced and communicated guidance on contractors for all staff, along with a checklist | 
Human Resources | Lead, develop and implement HR and OD interventions as per the ‘People’ workstream and project plan to support the effective implementation of the organisational wide transformation programme ensuring that this is aligned with the organisational recovery plan | A step change to the way the organisation delivers its services through people |  |  | Further detailed information on the TOM is needed to enable the one team workstream to progress activities fully. In the interim, work has taken place to fully align the pay structures in the two councils from April 2021 (subject to agreement). Future working styles project to inform transformation is paused due to lockdown. Values and behaviours employee group created and in progress to review the values of the councils | 
 | Effectively deliver CSP18 Alpha project and all associated objectives and develop a business case for the future delivery of payroll | Delivery of a successful payroll for 2020-21 (people paid accurately and on time) and a business case which identifies an affordable fit-for-purpose future payroll solution |  |  | Plan to extend Zellis arrangement with South & Vale and Hart councils until April 2022. Cabinet paper and decision scheduled for mid February | 
Corporate Action Plan 2020-21
Organisational Development

## Slide 20: Programmes, Redesign & Quality Head of Service: Sue Parker
Incorporating: Business Solutions Unit, Digital Design, Information Governance, Governance Hub, Effective Working, Facilities Management
Indicator | Target | Q1 | Q2 | Q3
Freedom of Information - number of requests received | N/A | 84 | 120 | 138
Freedom of Information - requests completed within 20 day statutory deadline (%) | above 95% | 98.8% | 97.5% | 96.4%
Environmental Information Regulations - number of requests received | N/A | 33 | 51 | 48
Environmental Information Regulations - requests completed within 20 day statutory deadline (%) | above 95% | 87.9% | 94.1% | 95.8%
Subject Access Requests - number of requests received | N/A | 2 | 2 | 0
Subject Access Requests - requests completed within statutory deadline of one month (%) | above 95% | 100% | 100% | N/A
Key Performance Indicators
Variance of £4,000
Budget variance in Q3
Chart: 
| Q1
Budget | -2940
Estimated outturn | -2944

## Slide 21: Programmes, Redesign & Quality
Team | Action | Outcome | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Business Solutions Unit | Develop and deliver discovery phase of transformation | Robust and evidenced approach in place for the implementation phase of transformation |  |  | Critical friend review of the overall programme so far has been ongoing, with feedback presented to EB. Discovery work has continued and is now progressing well, but is behind planned timescale. Current discovery activity is focusing on extracting a breadth of high level information from service areas | 
 | Design and deliver transformation implementation plans for the Council | Opportunities for service redesign are identified and implemented, leading to better use of resources and enhanced service delivery in line with need |  |  | There has been no further work carried out on the Design & System Implementation Programme (apart from Building Control) during this quarter, pending design of the Transformation workstreams. As the critical friend feedback on the Shaping our Future programme is reviewed and resulting actions decided, discussions have commenced regarding the approach and best fit for DSIP and whether to recommence as standalone or integrate to Shaping our Future | 
 | Ensure project and programme management resources are focused on corporate priorities | Skills and resources applied to enable successful delivery of corporate priorities |  |  | Delay to progress on Transformation programme has relieved some of the pressure for BSU resources. There is a continued focus on priority projects. Development of a portfolio management approach to assist with prioritisation and resource allocation process has commenced during this period. The BSU have also carried out reviews of their own ‘Ways of Working’ and have identified actions that will be key to providing effective support to the corporate projects and programmes | 
Digital Design | Design and deliver 2020 digital projects, informed by the digital design guidelines of the Digital Strategy and the transformation plans for the Council | Digital solutions enabling the Councils' strategic and operational priorities, namely: desktop hardware refresh, productivity tools, case management solutions |  |  | Work has been completed to develop the Transformation strategy map for digital infrastructure as part of the Transformation programme expanding upon the stages, guidelines and projects detailed within the Digital Strategy. Packaging for the CMW environment is near completion to support the CVW decommission. An upgrade to older device types in January will ensure base devices are fit for new applications | 
 | Deliver agreed 5C IT service adjustments in liaison with 3rd party and Client Team | Improvements unlock opportunities for digital enablers as required via transformation plans for the Council |  |  | The councils have now begun an interim approach in order to progress with Transformation planning and implementation. Delayed delivery of technical proposals and subsequent 5C negotiation to separate the shared Microsoft tenancy have forced the council to initiate their own project to take advantage of cloud infrastructure opportunities | 
Governance Hub | Embed proactive performance management across the organisation, providing a refreshed suite of performance indicators and tools to promote accountability and transparency | Timely, meaningful reporting to different audiences. Performance management process is seen to add value to day-to-day work. At service level, success is recognised appropriately and interventions can be targeted where required |  |  | Quarterly performance reports are now being shared with all staff via Team Talk Unfortunately as the Covid situation deteriorates, pressures within services continue to delay planned improvements to KPIs | 
 | Maintain and improve understanding of the cycle of corporate governance activities, including quarterly performance reporting, risk management, and production of the Annual Governance Statement | Understanding of corporate governance is strong Evidence-based insight is an integral part of decision making |  |  | Targeted training sessions on report writing and the decision making process were run in November with very positive feedback and a summary of the feedback and lessons learned has been provided to EB as part of the HoS review of the decision making process. Work has begun on redeveloping the governance content on the intranet, with the aim of providing a comprehensive, relevant, easily understandable self-service resource. Annual Governance Statement for 2019-20 has now been published alongside the Annual Statement of Accounts | 
Information Governance | Address management actions associated with the 2019-20 audit | Effective mitigation of risks associated with poor compliance with information governance legislation, thereby protecting the Council against the risk of fines and negative reputation |  | complete | Complete | complete
 | Increase levels of understanding of responsibilities for information governance processes and controls | Improvement in the presence of necessary controls within services, reducing reliance on the Data Protection Officer |  |  | There has been a decrease in the number of outstanding Privacy Notices. There are now 2 outstanding and the relevant HoS will be required to report to January’s Corporate Governance Board | 
Workplace & Logistics | Redefine accommodation requirements in light of 'new BAU' requirements, transformation plans and digital enablers | Improved use of assets and new BAU in place across services |  |  | Utilisation of both sites has been undertaken against the backdrop of another lockdown in November and the challenges faced to ensure that colleagues could work in safe bubbles when on site. In today’s environment, best use of space is defined as ensuring colleagues who need to access site based services and systems are as safe as possible to do so and clear operational rules are in place | 
 | Manage partnership relationships to ensure future use of assets and collaborative working aligns with the transformation plans of the Council | Plaza operations and partner cooperation deliver a joined up new BAU to benefit the customer |  |  | Partners continue to work remotely. DVLA decided not to renew their licence for single desk on ground floor in light of their ability to work remotely since Covid situation arose. Also need to now consider the implications of finance services returning from Capita and redrawing the red line area they presently occupy as staff will become HBC employees and up to 10 desks will be vacated | 
 | Define and implement marketing strategy to re-establish income streams associated with the Plaza conference suite | Income returns to pre-pandemic level |  |  | Conference centre remains closed through Q3 and with lockdown now beginning the income expected from the conference centre will not be possible. Loss of income reflected in Covid cost spreadsheets | 
Corporate Action Plan 2020-21

## Slide 22: Strategic Commissioning Head of Service: Claire Hughes
Indicator | Target | Q1 | Q2 | Q3
Number of missed bins | Less than 35 per 100,000 | 167 | 345 | KPI under review
Percentage of household waste recycled and composted | Above 30% | 32% | 37% | 28%
Contamination of recycling (%) | Less than 10% | 19.3% | 21.2% | 19.0%
Number of fly tips reported | Less than 120 | 199 | 352 | 282
Key Performance Indicators
Budget variance in Q3
Corporate Action Plan 2020-21
Action | Outcome | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Review implications of the Environment Bill and identify mitigations to Hampshire County Council’s proposals on the future of waste disposal services | Clarity on future direction and obligations of the waste collection service |  |  | County wide briefings took place during the quarter and work at local and county level is progressing on schedule | 
Increase commercial activity by Norse South East to increase rebate to HBC | Income generated for the authority |  |  | Coronavirus continues to impact on the company’s ability to search for and secure commercial work. The trade waste service is continuing to grow as is the commercial work Norse does for schools and parishes in East Hampshire | 
Review delivery of the Capita contract and report on findings by December 2020 | Report prepared by end of Q3 |  |  | Negotiations concluded and report submitted to Cabinet for the resolution of outstanding disputes, milestones and volumetrics, and the removal of Exchequer and Procurement services from the contract. Procurement successfully withdrawn from the contract on 31st December 2020 | 
Incorporating: Capita, Environmental Services (Norse), Leisure
Variance of £225,000
Chart: 
| Q1
Budget | -4321
Estimated outturn | -4456

## Slide 23: Regeneration & Place dashboards
Performance information for Q3
Coastal Partnership
Housing & Communities
Neighbourhood Support
Planning
Property
Regeneration & Economy

## Slide 24: Coastal Partnership Head of Service: Lyall Cairns
Budget variance in Q3
Corporate Action Plan 2020-21
Team | Action | Outcome | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Coastal Partnership | Implement the asset investment programme (engineering maintenance and replacement works) in order to protect our coastline and reduce and manage coastal erosion and flood risk to our residents | HBC assets protected through regular and efficient maintenance Reduced flood risk, protecting the environment and residents |  |  | West Beach groyne emergency works completed and seeking cost recovery from the Environment Agency, value £35,400. Asset repairs have been reprioritised to reflect Covid 19 restrictions and the restricted bird wintering season. Works being prioritised based on risk include South Hayling beach management activities (potential requirement to recycle shingle from the open beach back onto depleted bays fronting Eastoke Corner only). It is anticipated that the 2020/21 groyne repair works will likely extend into 2021/22 | 
 | Implement coastal asset inspection and survey programme in line with SLAs and other commissions | Topographic surveys carried out for the regional monitoring programme and asset inspections (informing the asset investment plan programme and proactively contributing to delivery of projects to manage flood and erosion risk, future studies and assessment of climate change impacts). Commissions for land based surveys - supporting wider Council projects and providing a potential source of income |  |  | Coastal asset inspections are 90% complete, while slightly behind programme. Resources remain focused on the highest risk assets at West Beach, Eastoke, Langstone and Broadmarsh. Regional monitoring programme has recovered lost time and is now completed. This concludes Phase IV of the four year programme which has been delivered on time and budget. We are pricing Phase V, which will be a six year programme of survey work. Commissions for land surveys significantly reduced during Q1, were slowly recovering in Q2, but are again under pressure due to lockdown in Q3/4 and limited to ‘safety critical’ work only. The team has shifted to additional chargeable work for CP Capital projects and CELT, including significant UAV flights. Survey marketing is ongoing via email, webpage and promotional video | 
 | Identify and deliver the feasibility, option appraisal and EA funding to support future Coastal projects | Feasibility studies and appraisals to outline design of FCERM schemes which will help reduce the risks to people and the developed and natural environment from flooding and coastal erosion |  |  | Langstone FCERM Outline design study has now been completed. In October 2020 HBC Cabinet approved the outline designs and gave the formal decision to proceed into detailed design and procure professional consultant support. Detailed design procurement is underway with the next phase of the project due to start in earnest in March/April 2021. Significant funds have been raised towards project from CIL, RFCC levy and other sources continue to be investigated. Polarised community views remain. Hayling Island Coastal Management Strategy: Over the past quarter there has been significant engagement with landowners and key stakeholders with several meetings taking place to gather information and understand others aspirations for Hayling. This information will feed in to the option development process alongside all the other drivers for the strategy. Broadmarsh Outline Design Study – Funded by HBC and RFCC levy. Shortlisting and economic assessment completed and leading option identified. Further work surrounding broader outcomes is being investigated. Currently reviewing project outputs and beginning internal briefing process. Strong input into local and national groups to influence and shape our industry for the betterment of our communities – Southern Coastal Group, Local Government Association Special Interest Group. Key topics being influenced via Call to Arms documents for – Coastal Landfill, Asset Maintenance, Coastal Adaptation, Place Making and Funding | 
 | Deliver expert environmental advice/support to assist delivery of the Coastal Partnership projects and promote environmental enhancement opportunities | Provision of fabulous outdoor spaces as part of the coastal projects delivered, which will enable communities to enjoy the coastline and have improved open spaces for future generations to enjoy |  |  | Strong environmental support to option appraisal and outline design projects including Langstone, Broadmarsh, Hayling Island Beach Management Plan, and West Beach; regional habitat creation programme updated annually to identify opportunities within the Solent to improve and enhance the natural environment; ecological surveys completed as required for projects across the Borough; strong research and investigation into environmental and ecological enhancement for future project delivery | 
Civil Engineering & Landscape | Develop a sustainable transport network for walking and cycling | A sustainable transport network that allows residents to improve their quality of life by being healthier and more active in a safe environment |  |  | Reopening high streets continues to aid shoppers to be able to social distance when in our town centres. We are working with HCC to find funding to make the Emsworth town centre social distancing area a more permanent feature. Work also continues on a number of walking and cycling projects across the borough | 
 | Undertake HBC highway asset inspections as per programme | HBC assets will be protected through regular and efficient maintenance to ensure that the built environment is safe for the public to use |  |  | All HBC asset inspections are up to date as per inspection programme | 
 | Develop and sustain a transport network that is fit for purpose and will last beyond the Local Plan | A transport network that will encourage and sustain business growth |  |  | Transforming Cities project continues and we are working with HCC on the detailed design on the projects in the Havant area | 
Variance of £10,000
Chart: 
| Q1
Budget | -145
Estimated outturn | -155

## Slide 25: Housing & Communities Head of Service: Tracey Wood
Indicator | Target | Q1 | Q2 | Q3
Affordable homes delivered | above 130 (year end cumulative) | 0 (but none expected) | 0 | 15
Number of homelessness acceptances | below 65 (year end cumulative) | 1 | 1 | 1
Number of homelessness interventions | above 1050 (year end cumulative) | Worked with 254 cases during Q1, 96 of these were successful DHP claims | Team worked with 237 cases | Team worked with 194 cases
Key Performance Indicators
Budget variance in Q3
Variance of £102,000
Chart: 
| Q1
Budget | -1173
Estimated outturn | -1275

## Slide 26: Housing & Communities
Team | Action | Outcome | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Housing (Options & Advice) | Deliver year 1 of the Homelessness and Rough Sleepers Action Plan | Reduction in the number of households placed into B&B and outside the area Completed review of the private sector offer to maximise options for those facing homelessness Increased number of landlords we work with Number of HRA assessments carried out Number of preventions Relief given Completed review of the temporary accommodation offered to ensure best use of stock, reducing the need for B&B leading to a reduction in spend |  |  | Following a second lockdown in November, numbers in B&B remain high with no move-on accommodation being available | 
 | Deliver the Rough Sleepers Initiative 2020/21 (£92,000 joint project with EHDC) | Relevant 1.5 officers to deliver the initiative employed by June 2020 Reduction in the number of rough sleepers in the area Working with any rough sleepers identified or sofa surfers and providing options to them (deposits/mobile phones etc) |  |  | Delayed due to Covid 19 | 
Community | Work in partnership to develop a range of projects which aim to tackle health inequalities, securing external funding where appropriate | Get Up & Go project developed, with an aim to continuation of funding September 2020 Priorities on a ward by ward basis identified through the capture of data working with Public Health and CCG by June 2020 Healthy Havant media campaign developed by December 2020 Vulnerable communities in Wecock Farm, Hayling West, Stakes and Leigh Park supported in partnership and by identifying external funding opportunities |  |  | Focus on Covid response due the quarter has resulted in delay in progressing these items as community team are working with the community on Covid response | 
 | Implement the Open Space Strategy, securing funding to deliver recommended actions which will improve sport, leisure and play facilities in the Borough of Havant | Contract information and tender prepared for works to deliver the Play Investment Programme, with all works completed by end of March 2021 All works identified to be funded by CIL delivered by end of March 2021 Future projects for 2021 identified and CIL bids prepared by August 2020 |  |  | On track | 
 | Develop a multi-team approach to investigate ways to rationalise Council-owned community assets | Initial project team set up by end of July 2020 Project Initiation Documentation (PID) developed and actions agreed with Director and Cabinet Lead Events on Council land are delivered safely |  |  | Put on hold | 
 | Develop an implementation plan to ensure agreed S106 contributions for Community posts relating to new developments are allocated appropriately | Information relating to future contributions acquired by September 2020 Forecasting document regarding phased payments developed by December 2020 Recruitment plan agreed by March 2021 |  |  | Work has progressed on this with the manager reducing hours and officers being moved on a temporary basis to EH team for support | 
Corporate Action Plan 2020-21

## Slide 27: Neighbourhood Support Head of Service: Natalie Meagher
Chart: 
| Q1
Budget | 317
Estimated outturn | -730
Incorporating: Environmental Health, Neighbourhood Quality, Parking & Traffic Management
Indicator | Target | Q1 | Q2 | Q3
Parking and traffic - income from pay and display machines (£) | above £265,710 | £259,561 | £606,212 | £305,026
Parking and traffic - income from Penalty Charge Notices (£) | above £57,359 | £5,147 | £38,822 | £57,564
Parking and traffic - FPN collection rate (%) | above 60% | Not reported by service | Not reported by service | Not reported by service
Public health funerals – number of burials | N/A | N/A (new KPI) | 10 | Not reported by service
Public health funerals – total costs (£) | N/A | N/A (new KPI) | £10,929 | Not reported by service
Public health funerals – recovery of costs (%) | TBC | N/A (new KPI) | 59% | Not reported by service
Pest control – total income (£) | TBC | N/A (new KPI) | £5109 cumulative | Not reported by service
Private sector housing – total number of DFG cases approved and completed | N/A | N/A (new KPI) | 20 | 27
Private sector housing – DFG cases (minor adaptations) completed within time limit of 90 days from valid referral (%) | TBC | N/A (new KPI) | N/A (new KPI) | 72%
Private sector housing – DFG cases (complex adaptations) completed within time limit of 120 days from valid referral (%) | TBC | N/A (new KPI) | N/A (new KPI) | 43%
Private sector housing – total DFG spend (£) | N/A | N/A (new KPI) | £259,256 cumulative | Not reported by service
Additional indicators will be added in Q4 |  |  |  | 
Key Performance Indicators
Budget variance in Q3
Variance of £1,047,000

## Slide 28: Neighbourhood Support
Team | Action | Outcome | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Environmental Health | Undertake a resourcing review for the licensing service | A service developed to suit the current climate for the licensing function which is responsive, dynamic and aligned across EHDC and HBC |  |  | No change to previous quarter, although recruitment to two vacancies has been completed. New starters due to commence in Q4 | 
 | Seek and gain approval for additional resource to support effective delivery of Disabled Facilities Grants, at no additional cost to the Council | Additional resource for the Private Sector Housing team which brings a unique skillset increasing effective delivery of DFGs and addressing the needs of some of the most vulnerable in our communities |  |  | No change from previous quarter | 
Neighbourhood Quality | Review, align and formally adopt the Enforcement Plan | A plan which supports best practice, is deliverable and responds effectively to customer demand Wherever possible, processes aligned across both Councils |  |  | Revised plans have been approved by Portfolio Holders. Plans now ready for publication. Action closed | complete
Parking & Traffic Management | Undertake and implement a review of permits | A suite of permit schemes which are (cost) consistent with HCC's on street scheme A scheme which promotes the green agenda and is straightforward and attractive to customers |  |  | Existing permits have been reviewed as part of budget setting process. Recommendations for amendments will go live in April, subject to the budget being approved | 
Corporate Action Plan 2020-21

## Slide 29: Planning Interim Heads of Service: Julia Mansi and David Hayward
Incorporating: Development Management, Planning Policy, Building Heritage, Building Control
Budget variance in Q3
Key Performance Indicators
Indicator | Target | Q1 | Q2 | Q3
Number of non-compliances found under the LABC Quality Management Scheme registered under ISO 9001:2015 (internal review) | 0 | N/A (new KPI) | 2 | 0
Number of previous non-compliances under the LABC Quality Management Scheme reviewed and resolved | Number of non-compliances found in previous quarter | N/A (new KPI) | 0 | 2
Number of claims submitted against the Council for Building Control negligence / non-compliance that the Council was unsuccessful in defending | 0 | N/A (new KPI) | 0 | 1 With Local Government Ombudsman to decide
Number of Building Regulations projects commenced under the Council’s control | N/A | N/A (new KPI) | 157 | 145
Number of Building Regulations projects completed under the Council’s control | N/A | N/A (new KPI) | 108 | Not able to report
Dangerous structures receiving an initial risk assessment within 24 hours of report being received (%) | 100% | N/A (new KPI) | 100% | 100%
Full Plans applications decided within statutory time limit (%) | 100% | N/A (new KPI) | Not able to report due to back office system migration | Not able to report due to back office system migration
Full Plans applications checked within 15 days (%) | above 90% | Not able to report due to back office system migration | Not able to report due to back office system migration | Not able to report due to back office system migration
Continued on next slide
Variance of -£234,000
Chart: 
| Q1
Budget | -856
Estimated outturn | -622
Notes: Building Control claims: complaint regarding wrong foundation advice which led to additional costs. Currently with Local Government Ombudsman to decide

## Slide 30: Planning
Indicator | Target | Q1 | Q2 | Q3
Major planning applications - number decided | N/A | 4 | 4 | 4
Major planning applications - % decided within 13 weeks or agreed time extension | above 70% | 100% | 100% | 100%
Minor planning applications - number decided | N/A | 22 | 20 | 22
Minor planning applications - % decided within 8 weeks or agreed extension | above 65% | 82% | 85% | 85%
Other planning applications - number decided | N/A | 109 | 126 | 129
Other planning applications - % decided within 8 weeks or agreed extension | above 80% | 92% | 94% | 91%
All applications - % decided within 26 weeks | above 98% | 99% | 99% | 99%
Discharge of condition applications - % decided within 8 weeks | above 80% | 26% Conditions Officer post currently vacant | 72% | 35% Conditions Officer post remains vacant
Major planning applications - % of decisions allowed on appeal | below 20% | 0% | 0% | 0%
Minor and other planning applications - % of decisions allowed on appeal | below 30% | 0% | 0% | 0.5%
Key Performance Indicators

## Slide 31: Planning
Team | Action | Outcome | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Building Control | Implement service review to form a shared workforce across Havant and East Hampshire, with a model that is scaleable to take on additional Building Control business where the opportunity arises | One workforce team for Building Control across Havant and East Hampshire created |  |  | Service review complete on 2nd November. All staff now part of new One Workforce team | complete
 | Review and amend Building Control prices to ensure full cost recovery against chargeable work and implement time recording system to assist future pricing reviews | Fair and transparent fees with strong evidence in place |  |  | Prices reviewed and amended with full evidence in place, ready to implement from 1st April 2020 (subject to Council approval of the proposed new hourly rate) | complete
 | Continue and complete the implementation of the new Tascomi Building Control system and review the actual benefits attained against perceived ones | New IT project completed and report published on benefit realisation |  |  | The data export / import issues previously identified are still outstanding. Staff have been working with external suppliers to resolve outstanding matters and the data import and testing is now due in January 2021 | 
Development Management | Ensure timely decision making of major applications | Delivery of high quality housing and employment development Delivery of affordable housing |  |  | Service working normally with most staff working remotely. DMC meeting as normal and making decisions. Applications submitted at an all time high – staff starting to struggle with workloads. Recruiting to two vacant posts | 
 | Seek best possible placemaking outcomes for developments | Delivery of infrastructure and facilities is facilitated The quality of place is preserved, protected or enhanced |  |  | Service working normally with most staff working remotely. DMC meeting as normal and making decisions | 
 | Replace existing IT system | Provision of improved and more efficient service for customers Team performance retained and enhanced |  |  | Waiting to see how this fits with transformation and corporate support. Project ready for next phase | 
Planning Policy | Undertake the consultation on changes to the Havant Borough Local Plan and submit the plan to government for examination | A submitted Local Plan that has increased weight in decision making |  | Not reported | Consultation took place November-December 2020 | 
 | Put in place a complete mitigation plan to ensure development is nutrient neutral, using HBC landholding, which is financially sustainable to the Council | A mitigation plan prepared and in the process of being implemented |  | Not reported | LEP grant must be spent by end of financial year, otherwise funding will be withdrawn and reputation with LEP damaged. Mitigation scheme is up and running and successfully being implemented | 
 | Undertake a comprehensive review of the Community Infrastructure Levy Spending Protocol | An adopted Community Infrastructure Levy Spending Protocol |  | Not reported | 2020/21 spending round is progressing – Cabinet briefing on 13/1. Members highlight this as being extremely controversial. Questions remain over the future process, to be set out in the spending protocol, and resources to enact it | 
Corporate Action Plan 2020-21

## Slide 32: Property Interim Head of Service: Natalie Meagher
Key Performance Indicators
Budget variance in Q3
Corporate Action Plan 2020-21
Action | Outcome | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Develop, deliver and implement a new staffing structure across both Councils | A team that is appropriately resourced and possesses the right skillset, experience and expertise to meet the Councils' aspirations in terms of estates and asset management |  |  | Lead Asset Manager has been recruited, due to start in April 2021. Recruitment underway for remaining 4 posts: Lead Estate Manager, Estate Manager, Senior Estate Surveyor and Asset Manager | 
Variance of £199,000
Chart: 
| Q1
Budget | 1430
Estimated outturn | 1231
Quarter | Billed | Collected | %
Quarter (25 March-24 June) | £469,008 | £453,880 | 96.8
Quarter (25 June – 27 September) | £435,367 | £428,811 | 98.5
Quarter (28 September – 30 December) | £430,920 | £425,820 | 98.8
Quarter (31 December – 24 March) | £427,388 | £343,398 | 80.3
Notes: Meridian and rest of HBC portfolio reported separately on weekly basis. At end of Q2, total debt less than 3% on HBC estate (exc Meridian). Rent recovery at Meridian = approx 67%. Parking income down > 70%

## Slide 33: Regeneration & Economy Head of Service: Clare Chester
Variance of -£19,000
Budget variance in Q3
Corporate Action Plan 2020-21
Team | Action | Outcome | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Regeneration South | Bring forward the five strategic development areas set out in the Regeneration Strategy with a particular focus on the synergistic opportunities around Havant town centre, Leigh Park centre and Hayling seafront | TBC |  |  | The review of the Regeneration Strategy with members concluded that the regeneration of Havant town centre should remain a priority. The project relating to Civic Plaza Car Park is being closed and a Cabinet report has been drafted to this effect. Marshall Regeneration Ltd have been commissioned to set out a project relating to the wider Civic Plaza and town centre in light of reduced resources | 
 | Deliver the Regeneration Programme, continuing to build on the themes established in the Regeneration Strategy | Individual projects will be taken to Cabinet for approval. The Regeneration Programme, including progress, will be reviewed every three years |  |  | Brockhampton disposal exchanged on 20th December 2020 and due to complete on 11th January 2021. This is phase 1 of the Regeneration Strategy that generates significant capital funding to take forward future phases | 
 | Identify, through engagement, where projects can be developed to provide direct stimuli into the local economy and community | TBC |  |  | Priorities agreed with members particularly around the allocation of capital funds. Programme Manager submitted resignation meaning that resources and delivery will need to be reviewed | 
Economic Development | Implement the business and economic development priorities within the Covid-19 economy recovery programme | Businesses are supported with grant funding advice and support to remain operational/solvent during the Covid-19 outbreak and thriving in the long term |  | Not reported | Team have been working with businesses across the Borough to ensure that grants are available to businesses | 
Incorporating: Regeneration South, Economic Development
Chart: 
| Q1
Budget | -440
Estimated outturn | -421