## Slide 1
Havant Borough Council Performance Report
Q3 2021-22
V1

## Slide 2: Contents
Headline achievements for Q3
People – key statistics for Q3
Finance
Corporate governance – key statistics for Q3
Service dashboards (containing in-depth information about Corporate Action Plan objectives, KPIs, and budget variance)
    Strategy Unit
Corporate Services
Regeneration & Place

## Slide 3: Headline achievements in Q3
Havant Borough Council were awarded nearly £500,000 to fund a scheme to help young people in Leigh Park into work and improve their long-term health and wellbeing.
A new play area was opened in Emsworth Recreation Ground and progress has been made on the refurbishment of the Jubilee Park play area in Waterlooville
Local entrepreneurs were also given a boost with a free week-long course from Rebel Business School that was funded by several local councils​
A survey of residents shows that trust in information and advice provided by HBC has remained high throughout the pandemic at 81%, particularly when compared to the national average of 54%

## Slide 4: People – key statistics for Q3
Number of new starters
Total FTE at end of quarter
Average number of sick days per FTE
Public sector average: 2.2 days Private sector average: 1.8 days
Number of leavers
Turnover rate
1.8
233
7
9
3.8%
Reported sickness levels remain below the national average for the public sector
Notes: Turnover rate is calculated as the number of leavers as a % of the total FTE
We are now separating short term and long term sickness to be able to understand the most common reasons for sickness without the data being skewed by a small number of staff being off for a large number of days (e.g. for operation/recovery). Short term sickness is defined by the HR team as less than 21 days
Average number of sick days per FTE still includes both short and long term sickness
It should also be noted that these figures relate to those staff who are employed by HBC and therefore may not provide an accurate picture when comparing to the EHDC figures given that many staff are shared across both organisations and which authority they are employed by is largely a matter of chance.

## Slide 5: Finance – revenue budget outturn in Q3
 | Full Year Budget | Q3 Year End Forecast | Q3 Variation to Budget
 | £'000 | £'000 | £'000
Net Cost of Services | 13.593 | 13.804 | 0.211
Funding | (13.593) | (13.593) | 0.000
Net (Surplus) / Deficit | 0 | 0.211 | 0.211

## Slide 6: Corporate governance – key statistics for Q3
 | Number of complaints received | % of complaints resolved within 10 working days Target: 85%
Waste | 237 | 59%
Revenues and Benefits | 26 | 100%
Environmental Health including Pest Control and Licensing | 2 | 0%
Planning | 12 | 58%
Parking and Traffic | 4 | 100%
Other | 5 | 80%
110
Number of internal audit management actions overdue by more than 60 days
7
Number of information requests received
(Freedom of Information, Environmental Information Regulations and Subject Access Requests)
Number has now stayed roughly consistent for several quarters in a row
Significant improvement since Q1 position (41)
Arrows indicate trend vs. Q2
Notes: Most common areas for complaints in Q2 were:
Number of information requests has increased by 45% compared to Q1 – this is perhaps due to the easing of lockdown leading to more activity in economy, housing market, local politics etc

## Slide 7: Risks currently scoring above 16 on the corporate risk register
A residual score of 16 is the threshold which has been set to indicate the Council's risk appetite (as per the Risk Management Framework).
Risk ID | Risk Title | Type | Category | Identification of areas where there are significant risks | Date Added | Risk Owner | Original Assessment |  |  | Planned Mitigation Actions | Mitigation Success Factor | Control Assessment |  | 
 |  |  |  |  |  |  | L | I | P |  |  | L | I | P
HB6 | Medium Term Financial Strategy | FINANCIAL | Economic | The ongoing viability of the authority being able to manage a balanced budget. Current MTFS highlights a shortfall of £12M over the course of the MTFS | 28/11/16 | Lydia Morrison | 4 | 5 | 20 | 1. MTFS is reviewed each year as part of budget setting exercise. Budget challenge sessions held each year to scrutinise future business plans and income/savings. 2. Full MTFS review to take place in 2020/21 to alongside the Transformation programme 3. Identify and manage in-depth service budgets income/expenditure to rebalance budget 4. Consider the impact of Covid-19 on the MTFS | The authority has a balanced budget | 4 | 4 | 16
HB9 | IT provision: long term | SERVICE | Technological | Failure by the IT provider (Capita) to deliver on long term digital vision and aspirations of Council as per the contract in particular the strategy for 'digital by default' and contract requirements | 10/04/18 | Sue Parker | 5 | 5 | 25 | 1. Ensure Capita are held to contractual responsibilities regarding digital strategy 2. Progression of a Digital Strategy for the Council as part of SoF with linkages to IT Capita 3. Deliver changes to the IT infrastructure to enable SoF outcomes e.g. M365 segregation | Clear vision and links to Council aspiration of 'digital by default' Approval of Council's Digital Strategy - October 2019. Approach is aligned to SoF outcomes | 4 | 4 | 16
HB10 | Corporate Project Delivery | GOVERNANCE | Reputation | Failure to maintain control of corporate project delivery leading to lack of clarity on priorities, use of resources resulting in reputational damage and potential costs and potential adverse impact on performance. | 07/05/18 | Gill Kneller | 4 | 5 | 20 | 1) Establishment of Strategic Project Board for oversight of key corporate projects 2) Clear review of project milestones to ensure on track and delivering as per budget 3) Dedicated project budget monitoring - in particular Capital budget monitoring 4) All corporate projects have appropriate governance in place and regularly produce highlight reports 5) Review of Corporate projects to ensure focus and resource is on the right project areas covering Corporate Strategy, transformation and Covid-19 recovery | Corporate projects will deliver on time or be replaced by others with greater importance | 4 | 4 | 16
HB1 | Contractual Arrangements | FINANCIAL | Organisational | Risk of our contractors failing to deliver all/part of the contract leading to non delivery of service(s) to our residents. Early termination of all or part of the Norse SE JV by one of the 3 parties due to performance and/ or financial issues. Failure of the Norse SE JV to improve performance and financial management due to inadequate support. | 01/09/16 | Trevor Pugh | 5 | 5 | 25 | Environmental Services Service and Delegation Agreement 1) NSE Board regularly meets to review current performance 2) Key performance indicators in place and being monitored for waste operation 3) Provision of expert financial and operational support to review accounts and co-develop a detailed Business Plan for 2022 and beyond. 4) Strengthened JV Liaison Team and recruitment to cover vacancies. 5) Risk based approach to JV Liaison. 6) Exit strategy 7) Review of Governance | Contract delivers as per cost and performance. Previous years accounts and current budget agreed; monthly budget monitoring and forecasting satisfactory. Business Plan produced in line with Service Agreement requirements. Governance actions completed Internal audit actions completed. | 4 | 4 | 16
Likelihood has increased in Q3 due to stalling of Microsoft 365 proposals

## Slide 8: Strategy Unit dashboards
Performance information for Q3
Organisational Development
Programmes, Redesign & Quality

## Slide 9: Organisational Development Head of Service: Caroline Tickner
Incorporating: Human Resources, Communications & Marketing, Emergency Planning & Business Continuity, Health & Safety
No variance
Budget variance in Q3
Corporate Action Plan 2021-22
Chart: 
| Q1
Budget | -724
Estimated outturn | -724
Project/strategy | Objective | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Interim workstyle solutions | Approach to co-ordinate next steps for new ways of working for reception and back office in Penns and Plaza |  |  | Report submitted to EB and discussed re future working styles. Trial and post-trial survey due to end Jan 2022. Overall report including policy will be developed to implement from Q1 22/23. | 
Communications service review | Consideration of a business case as per budget challenge proposal |  |  | Business case and proposals taking account of the SoF programme are awaiting sign off by Executive Board. Budget challenge for 21/22 re salary savings has been met due to vacancy savings. | 
Indicator | Target | Q1 | Q2 | Q3
Number of website visits | N/A | 113,000 | 155,000 | 115,000
Key Performance Indicators

## Slide 10: Programmes, Redesign & Quality Head of Service: Sue Parker
A small number of complex EIRs have affected performance in Q3
Incorporating: Business Solutions Unit, Digital Design, Information Governance, Governance Hub, Effective Working, Facilities Management
Indicator | Target | Q1 | Q2 | Q3
Freedom of Information - number of requests received | N/A | 126 | 119 | 110
Freedom of Information - requests completed within 20 day statutory deadline (%) | above 95% | 95% | 96% | 95%
Environmental Information Regulations - number of requests received | N/A | 26 | 37 | 32
Environmental Information Regulations - requests completed within 20 day statutory deadline (%) | above 95% | 100% | 84% | 94%
Subject Access Requests - number of requests received | N/A | 4 | 3 | 3
Subject Access Requests - requests completed within statutory deadline of one month (%) | above 95% | 75% | 100% | 100%
Key Performance Indicators
No variance
Budget variance in Q3
Chart: 
| Q1
Budget | -3039
Estimated outturn | -3039
Project/ strategy | Outcome | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Digital Strategy | Numerous projects to deliver the strategy including foundation initiatives such as Sharepoint and transformation related priorities as informed by Shaping our Future |  |  | Multi Factor Authentication now to be delivered early Qtr 4 (end of January). Tenancy split proposal costly, and therefore approach is under review. High Level Design for Target Operating Model is complete, with detailed design to be completed with support and advice of 3rd party during early part of Qtr 4. | 
Review of Mayoral provision | Consideration of a business case as per budget challenge proposal |  |  | Scope for savings still under discussion with Leader and Mayor. % put forward as part of 22-23 budget setting process, likelihood of further savings subject to agreement in Qtr 4. | 
Corporate Action Plan 2021-22

## Slide 11: Corporate Services dashboards
Performance information for Q3
Customer Services
Finance
Legal
Strategic Commissioning

## Slide 12: Customer Services Head of Service: Brian Wood
Variance of £60,000
Budget variance in Q3
Incorporating: Corporate Support, Elections, Land Charges, GIS, Insight
Customer Services and Revenues and Benefits are provided by Capita
Indicator | Target | Q1 | Q2 | Q3
Calls answered and completed by CSC - one and done (%) | above 95% | 98.5% | 99.0% | 100%
Calls answered within 20 seconds in the CSC (%) | above 75% | 13.0% | 45.7% | 87%
Council tax cash collection rate - cumulative (%) | above 98.9% (year end cumulative) | 28.94% | 56.32% | 83.85%
Non domestic rates cash collection rate - cumulative (%) | above 98.6% (year end cumulative) | 18.21% | 43.60% | 72.77%
Average processing time - housing benefit and council tax benefit change events (days) | below 7 | 9.1 | 8.2 | 7.5
Average processing time - housing benefit and council tax benefit - new claims (days) | below 17 | 10.9 | 9.8 | 9.5
Key Performance Indicators
Chart: 
| Q1
Budget | -3231
Estimated outturn | -3171
Huge improvement due to better waste service performance and improved communications between Norse and Capita
Corporate Action Plan 2021-22
Project/ strategy | Objective | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Discretionary Rate Relief Schemes | Review of schemes (yearly requirement) |  |  | Fundamental review under way - review of approx 20 businesses to understand current circumstances - waiting for completed forms to review - Cabinet Lead briefed | 
CRM improvements | Development and implementation of customer portal |  |  | Change to plans - Business Case for Customer Portal at HBC to be included in full Business Case for Transformation - this will ensure that the requirements for the CRM / Portal match the overall IT design for Transformation. | 
Still off target due to a backlog of Universal Credit changes, but on a good trajectory

## Slide 13: Finance Head of Service: Matthew Tiller
Corporate Action Plan 2021-22
No variance
Budget variance in Q3
Chart: 
| Q1
Budget | -1040
Estimated outturn | -1040
Project/ strategy | Objective | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Finance service improvement | Service improvement work following return inhouse |  |  | New processes and procedures being revised and finalised. Roll out timetable being revised whilst we test robustness of procedures. | 

## Slide 14: Legal Head of Service: Daniel Toohey
Incorporating: Legal Services, Democratic Services
Variance of £40,000
Budget variance in Q3
Chart: 
| Q1
Budget | -913
Estimated outturn | -953
Further Corporate Action items and Performance Indicators are still under development by Head of Service and their team.

## Slide 15: Strategic Commissioning Head of Service: Trevor Pugh (ES)
Indicator | Target | Q1 | Q2 | Q3
Number of missed bins | Less than 35 per 100,000 | Due to national staff shortages, figures are not currently available |  | 180
Percentage of household waste recycled and composted | Above 30% | 25% | 17% | 20%
Contamination of recycling (%) | Less than 10% | Not reported by Norse | 16% | 17%
Number of fly tips reported | Less than 120 | 337 | 319 | 174
Key Performance Indicators
Budget variance in Q3
Corporate Action Plan 2021-22
Incorporating: Capita, Environmental Services (Norse), Leisure
Variance of £85,000
Chart: 
| Q1
Budget | -3855
Estimated outturn | -3940
Project/strategy | Objective | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Future waste collection / HCC negotiations | Environment Bill and HCC efficiency savings implications |  |  | Environment Act passed Nov 2021. Government response to relevant waste management consultations expected early 2022 with more clarity on requirements and timescales/ funding. Detailed modelling of waste collection service changes planned for April 2022. Draft revised HCC Memorandum of Understanding and Financial Agreement scheduled for Partnership Board February 2022. | 
Review of leisure provision | Negotiations over Horizon and future leisure provision |  |  | Draft Commercial Leisure Strategy has been created; this will now be taken to EB and Cabinet for approval. This Strategy will form the foundation of the relationship with the trust moving forward. | 
NSE commercial strategy | Oversight of Norse commercial strategy |  |  | Business Plan draft scheduled for end January 2022. | 
Data for Oct and Nov only
Total Oct and Nov

## Slide 16: Regeneration & Place dashboards
Performance information for Q3
Coastal Partners
Housing & Communities
Neighbourhood Support
Planning
Property
Regeneration & Economy

## Slide 17: Coastal Partners Head of Service: Lyall Cairns
Budget variance in Q3
Corporate Action Plan 2021-22
No variance
Chart: 
| Q1
Budget | -417
Estimated outturn | -417
Project/strategy | Objective | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Langstone Flood and Coastal Erosion Risk Management Scheme | Reduce flood risk to Langstone community and protect access to Hayling Island |  |  | Working toward the refinement of the design ahead of AECOM advancing the final options. Ground Investigations and Structural Investigations are completed and awaiting the interpretive reports. Prolongation of the programme agreed to give great time for community and stakeholder consultation. OBC Approved by Assurance and LAIDB. | 
Coastal Partners governance and business model review | Review of governance arrangements for partnership to ensure the service is fit for future |  |  | Draft Service Agreement issued by Legal on 21/12/21 to Chichester District Council and forwarded onto other Partners for review by Simon Jenkins. Awaiting feedback. | 
Warblington new pedestrian bridge (CELT led project) | Protection of pedestrians when crossing Warblington train line |  |  | • EB Approved Report • Cabinet Approved Report and funding | 
Hayling Island beach management activities and supporting studies | Manage flood risk to 1700 homes at Eastoke |  |  | January 2022 - Preparation for spring beach management campaign during March 2022, and potential small scale earlier campaign following beach erosion from storm events. | 
Broadmarsh Coastal Park and coastal Landfill Protection Project | Understand and respond to erosion risk to the coastal landfill at Broadmarsh |  |  | Following EB briefing in Oct 21, Cabinet Report currently being drafted to return to EB / Cabinet in Feb 22 | 
Hayling Island Coastal Strategy | Understand the flood and erosion risk to the Hayling Island coastline and develop a long-term strategic approach to implement the shoreline management plan policies |  |  | The draft coastal management options have been appraised. Will be preparing over the coming months for engagement with stakeholders and public in Spring / Summer on the draft Coastal Management Strategy. | 
Coastal survey programme | Implement coastal survey programme in line with SLAs – topographic surveys carried out for the regional monitoring programme to monitor coastal change and processes |  |  | Service Level Agreement approved by Cabinet. Proceeding to sign-off and then invoicing. | 

## Slide 18: Housing & Communities Head of Service: Tracey Wood
Chart: 
| Q1
Budget | -1038
Estimated outturn | -1038
Key Performance Indicators
Budget variance in Q3
No variance
Project/ strategy | Objective | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Community Engagement Strategy | Developing a community engagement strategy |  |  | Draft needs to be revised as is currently a joint strategy - also awaiting feedback from Locality in January to feed into the strategy/ies | 
Homelessness and Rough Sleeping Strategy | Implementation of Homelessness Strategy/Action Plan |  |  | Affordable Housing units 6. Worked with 188 homeless households. Annual Rough Sleeper count in Nov was 0. Currently working on Rough Sleeper Initiative bid to be submitted Feb 22 | 
S106 contributions | Implementation of plan to ensure S106 contributions for community posts are allocated appropriately |  |  | S106 post at HBC successfully recruited to Dec 21 | 
Review of play park provision | Review the provision of play parks. Review ownership, maintenance and develop a forward refurbishment plan of play area provision |  |  | Full report findings will be received end of Jan 22 - this will enable identification of those priority play areas to be refurbished, 3 each year. Emsworth play area refurbishment completed. 5 play areas have had pieces of equipment upgraded/replaced | 
Communities service review | Consideration of a business case as per budget challenge proposal |  |  | Temp arrangements remain in place until end of the year - Community Manager EH left the authority so there is a vacancy. Proposal was to have a shared team and manager. On hold | 
Corporate Action Plan 2021-22
Indicator | Target | Q1 | Q2 | Q3
Affordable homes delivered | above 130 (year end cumulative) | 16 | 29 | 6
Number of homelessness acceptances | below 65 (year end cumulative) | 3 | 0 | 0
Number of homelessness interventions | above 1050 (year end cumulative) | 178 | 219 | 188
Number of households in B&B | below 65 (year end cumulative) | 116 households spent time in B&B with 56 remaining at end of quarter | 60 households spent time in B&B with 43 remaining at end of quarter | 123 households spent time in B&B with 39 remaining at end of quarter
Number of weeks in B&B | Tracking | 275 | 402 | 475

## Slide 19: Neighbourhood Support Head of Service: Natalie Meagher
Chart: 
| Q1
Budget | 486
Estimated outturn | 426
Incorporating: Environmental Health, Neighbourhood Quality, Parking & Traffic Management
Indicator | Target | Q1 | Q2 | Q3
Parking and traffic - income from pay and display machines - cumulative (£) | above £1,614,000 at Q3 | £408,223 | £942,300 | £1,268,099
Parking and traffic - income from Penalty Charge Notices - cumulative (£) | above £246,300 at Q3 | £48,068 | £214,694 | £304,946
Parking and traffic - PCN collection rate (%) | Tracking | 59% | 58% | 59%
Public health funerals – number of burials / cremations | N/A | 4 | 1 | 1
Public health funerals – total costs (£) | N/A | £6,746 | £1,599 | £1,571
Public health funerals – recovery of costs (%) | Tracking | 24.78% | 0% | 0%
Pest control – total income (£) | TBC | £4,643 | £8,762 | £15,698
Private sector housing – total number of DFG cases approved and completed | N/A | In development | 27 | 19
Private sector housing – DFG cases (minor adaptations) completed within time limit of 90 days from valid referral (%) | Tracking | In development | 80% | 78%
Private sector housing – DFG cases (complex adaptations) completed within time limit of 120 days from valid referral (%) | Tracking | In development | 58% | 30%
Private sector housing – total DFG spend (£) | N/A | £304,182 | £459,478 | £627,998
Neighbourhood quality – number of fly tipping enforcement actions taken | Tracking | 19 | 50 | 30
Key Performance Indicators
Budget variance in Q3
Variance of £60,000

## Slide 20: Neighbourhood Support
Corporate Action Plan 2021-22
Project/strategy | Objective | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Outbreak Control Plan | Development of plan for potential future Covid outbreaks |  |  | Document under constant review in line with current government guidance / legislation regarding present Covid 19 situation. No further amendments to make at this time | 
Licensing service review | Resourcing review of service across both EHDC and HBC |  |  | No further changes to report in this quarter. Workload remains high and continues to increase. Need to establish a steady state within the service before this can progress. | 
Designated Public Place Orders | Review in light of new legislation |  |  | PSPO (previously DPPO) for alcohol has expired, to extend this evidence required to support a need for its' existence. No data to support so not extended. Seasonal restriction in place in bathing area between 30/05 & 01/09 within the current dog PSPO beach ban. This was renewed on the 1st of May 2021 and will be in place until 30th April 2024. Both elements completed and closed. | 

## Slide 21: Planning Interim Heads of Service: Julia Mansi and David Hayward
Incorporating: Development Management, Planning Policy, Building Heritage, Building Control
Budget variance in Q3
Key Performance Indicators
Indicator | Target | Q1 | Q2 | Q3
Number of non-compliances found under the LABC Quality Management Scheme registered under ISO 9001:2015 (internal review) | 0 | 1 | 0 | 0
Number of previous non-compliances under the LABC Quality Management Scheme reviewed and resolved | Number of non-compliances found in previous quarter | N/A (none found) | 1 | N/A (none found)
Number of claims submitted against the Council for Building Control negligence / non-compliance that the Council was unsuccessful in defending | 0 | 0 | 0 | 0
Number of Building Regulations projects commenced under the Council’s control | N/A | 180 | 170 | 153
Number of Building Regulations projects completed under the Council’s control | N/A | Not able to report due to back office system migration | 931 Including Competent Persons Scheme registrations | 215
Dangerous structures receiving an initial risk assessment within 24 hours of report being received (%) | 100% | 100% | 100% | 100%
Full Plans applications decided within statutory time limit (%) | 100% | Not able to report due to back office system migration | Not able to report due to back office system migration | 100%
Full Plans applications checked within 15 days (%) | above 90% | Not able to report due to back office system migration | Not able to report due to back office system migration | Not able to report due to back office system migration
Continued on next slide
Variance of £70,000
Chart: 
| Q1
Budget | -560
Estimated outturn | -630

## Slide 22: Planning
Recently appointed Discharge of Conditions Officer is still dealing with backlog of applications
Indicator | Target | Q1 | Q2 | Q3
Major planning applications - number decided | N/A | 4 | 3 | 6
Major planning applications - % decided within 13 weeks or agreed time extension | above 70% | 50% | 100% | 100%
Minor planning applications - number decided | N/A | 35 | 30 | 48
Minor planning applications - % decided within 8 weeks or agreed extension | above 65% | 77% | 93% | 90%
Other planning applications - number decided | N/A | 195 | 175 | 159
Other planning applications - % decided within 8 weeks or agreed extension | above 80% | 93% | 93% | 97%
All applications - % decided within 26 weeks | above 98% | 99% | 100% | 100%
Discharge of condition applications - % decided within 8 weeks | above 80% | 39% | 22.5% | 26%
Major planning applications - % of decisions allowed on appeal | below 20% | 0% | 2.5% | 3%
Minor and other planning applications - % of decisions allowed on appeal | below 30% | 0.37% | 0.29% | 0.38%
CIL and S106 agreements – monitoring fees collected | above £130,000 (year end cumulative) | £49,800 | £30,745 | £71,098
Key Performance Indicators

## Slide 23: Planning
Corporate Action Plan 2021-22
Project/ strategy | Objective | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
DSIP: Planning / Land Charges / Environmental Health system replacement | Procurement and implementation of replacement system (to replace Acolaid) |  |  | Project still paused pending work on TOM | 
Local Plan | Progress of production of Local Plan |  |  | At 17 January 2022, a response is awaited to the Council's letter to the inspectors on 17 December seeking a suspension of the examination until October 2022. Ideally the examination would be suspended until October 2022. If the inspectors do not accept this, a withdrawal of the local plan would be necessary, which will further delay getting a local plan in place. A paper will be considered by Full Council on 16 March formally recommending the way forward together with interim measures to address the increase in speculative planning applications that is inevitable as a result of this. Budget implications of this matter are feeding into the budget setting process. | 
CIL Spending Protocol | Comprehensive review of CIL Spending Protocol |  |  | The new protocol has been discussed internally with officers and put together. Cabinet Lead engagement has continued throughout. This will be considered by Planning Policy Committee towards the end of February and Full Council on 16 March. | 

## Slide 24: Property Head of Service: Clare Chester
Chart: 
| Q1
Budget | 1858
Estimated outturn | 1658
Key Performance Indicators
Budget variance in Q3
Corporate Action Plan 2021-22
Variance of £200,000
Indicator | Target | Q1 | Q2 | Q3
Rent arrears for all tenanted commercial property – average across quarter (£) | Below 10% of gross annual income (£2.395M) | £52,000 (due in quarter only) | £29,500 As at 7th Oct = 1.475% of annual rent | £150,703 (5.84% of gross annual rent)
Rent arrears over 90 days (aged debts) for all tenanted commercial property – at end of quarter (£) | Below 5% of gross annual income (£2.395M) | £361,000 (as at 2nd Sept) | £185,000 As at 7th Oct = 9.25% of annual rent | £359,770 (13.95% of gross annual rent)
Project/strategy | Objective | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Property management system | Procurement and implementation of new property management system |  |  | Procurement, Legal and technical specification ready to advertise to the market. Capita requested to quote for the cost and time to allow interaction and flow of information with finance and IT systems prior to procurement. Capita to be involved in advising on additional technical requirements. Additional capital funding likely required – funding sources being secured but current shortfall does represent a risk to the project. Firm figures only known through procurement process. | 
Estates and Facilities team options including accommodation | Consideration of business case as per budget challenge proposal |  |  | Limited progress due to other priorities. Will move forward as part of transformation. | 
Not directly comparable to Q1 & Q2. Includes Meridian Centre

## Slide 25: Regeneration & Economy Head of Service: Clare Chester
No variance
Budget variance in Q3
Corporate Action Plan 2021-22
Incorporating: Regeneration and Placemaking, Economic Development
Chart: 
| Q1
Budget | -562
Estimated outturn | -562
Project/strategy | Objective | Q1 RAG status | Q2 RAG status | Q3 update | Q3 RAG status
Review of shared Regeneration arrangements | Consideration of a business case as per budget challenge proposal |  |  | Joining of two teams now complete and working effectively. | 
Havant town centre redevelopment | Regeneration project |  |  | Levelling Up Fund bid unsuccessful, potential for future rounds. Consultants procured for viability assessments and master planning for Civic Plaza East and Bulbeck Road to take to Cabinet in Spring 2022. | 
Hayling Seafront Strategy | Regeneration project |  |  | First phase engagement programme completed in Nov 2021. Report to EB in Jan 2022 and a report is due to go to Cabinet spring 2022. | 
Regeneration Strategy | Review and refresh of Regeneration Strategy |  |  | The refreshed strategy is due to be taken to Cabinet and Full Council in March 2022. |